## Slide 1
Annex 5
to the Procedure for planning the work of the National Agency on Corruption Prevention based on the Objectives and Key Results (OKR) methodology for the implementation of the Mission "Building Integrity in Government and a Just Society (clauses 9, 10 of Section 2, paragraph 1 of Section 3)
Quarterly cycle of discussing and achieving OKRs
two weeks before the end of the quarter the last week of the quarter during the next quarter
OKR CYCLE 13 WEEKS
Discuss the progress of the Quarterly goals and their KR with the team
Set Quarterly targets for the next period within the framework of the previously set Annual targets
Jointly discuss Quarterly goals and their KRs and plans for the next quarter
(unit team + responsible person of the involved unit(s) + deputy + Head of the NACP)
Approval of the plan for the next quarter
During the next quarter, measure and discuss weekly progress on the Quarterly Goals and their KRs within the teams and in the last week of each month with the leader responsible for the Annual Goal
Add the draft quarterly goals and their KR to a single Google spreadsheet for the next quarter no later than the last day of the penultimate week of the quarter
Presentations of the current quarter's achievements and plans for the next quarter should be in a standard form (the current quarter is uploaded from Jira), but can be made in another form
The schedule of discussions is agreed with the receptions of the deputies and the Head
Preparing for the discussion:
The order of discussion: - 1 hour 30 minutes per unit team
Introduction from the head of the ISUs
Introduction of KR by those responsible for their achievements
Speech by each team member - up to 1 minute
Closing remarks by the team leader and the person responsible for the Annual Objective
The main questions to be answered by each team member and the teams of employees from other departments involved in KR
What was successful? What didn't work?
What should we do differently in the next quarter?
Ambitious and operational OKRs
The team can have both ambitious (part of the work plan) and operational OKRs (included in the civil servant's tasks)
What is important to remember when working with OKR:
At least 50% of the Quarterly Goals are proposed by the teams
Quarterly targets should be achievable in a quarter; Key results are measurable
No more than 3 ambitious Quarterly Goals per team with no less than 3 and no more than 5 Key Results in each
There can be no team without its own Key Result or Goal
Each OKR has a responsible person, who can be either a manager or a subordinate
If the Quarterly Goal does not have a co-executor, client, partner (the unit fulfils it independently), then it is not important for the organization